## Control
ID | Category | Test Name | Preconditions | Steps | Expected Result | Metrics / Threshold | Pass/Fail | Notes
CTL-001 | Control Channel | Agent connects and sends AgentHello | Agent has valid cert; Server reachable | Start agent; observe Connect() bidi stream establishment; capture first message | Server receives AgentHello with agent_id, version, platform, caps within 2s | T_conn<=2s
CTL-002 | Control Channel | Server can send StartOp and receive OpAck | CTL-001 passed | Server sends StartOp(file_get); wait for OpAck | Agent replies OpAck(accepted=true) with matching op_id | Ack_latency<=500ms
CTL-003 | Control Channel | Concurrency on single stream | Agent connected; configured to allow concurrency>=5 | Server issues 5 StartOp with distinct op_id quickly | Agent processes all; Server receives interleaved responses correctly grouped by op_id | No cross-op mix; 0 message loss
CTL-004 | Control Channel | Heartbeat liveness | Heartbeat period=10s configured | Simulate idle; ensure ping/pong exchanged | If 3 consecutive missed pong -> Server marks agent offline | Missed<=3; offline flag set at <=30s
CTL-005 | Control Channel | Duplicate StartOp idempotency | Existing op_id in-flight | Resend same StartOp(op_id identical) | Agent rejects duplicate: OpAck(accepted=false, reason=duplicate) | Consistent behavior; no duplicate execution
CTL-006 | Control Channel | Shutdown(draining) | One long-running op active | Server sends Shutdown(drain=true) | Agent completes active ops then closes stream | Stream closes gracefully; no data loss

## FileGet
ID | Category | Test Name | Preconditions | Steps | Expected Result | Metrics / Threshold | Pass/Fail | Notes
FIL-001 | FileGet | Happy path: full file streaming | Log file 100MB exists; path whitelisted | Send StartOp(FileGetSpec path=/var/log/app.log) | Receive ordered FileChunk(s) then OpEof with total_size & checksum | EOF.checksum==Server SHA256(file); throughput>=20MB/s on 1GbE
FIL-002 | FileGet | Chunk ordering and completeness | FIL-001 target file | Record offsets of each FileChunk | Offsets strictly increasing; no overlaps or gaps | No holes/overlaps
FIL-003 | FileGet | Compression on-wire | Same file as FIL-001 | StartOp with compress=true; capture network bytes | Data chunks are gzip-compressed; EOF.checksum equals original file checksum | Bytes_sent reduced >=30% for compressible logs
FIL-004 | FileGet | Checksum verification negative case | Corrupt file or tamper during transfer | Intentionally modify file mid-transfer (if safe) | Agent detects mismatch or Server-side checksum fails; test marked failure (expected) | Mismatch detected; proper OpError or audit log
FIL-005 | FileGet | Offset resume (断点续传) | Same 100MB file; start transfer and cancel mid-way | Resume with offset at last confirmed byte | Reassembled file equals original checksum | EOF.checksum match; no duplicated bytes
FIL-006 | FileGet | Path traversal defense | Agent whitelist=/var/log | StartOp with path=/var/log/../etc/passwd | Agent rejects with OpError(code=path_denied) | No read outside whitelist
FIL-007 | FileGet | Nonexistent file handling | Target file removed | StartOp to missing path | OpError(code=not_found) returned | Clear error semantics
FIL-008 | FileGet | Large file throughput baseline | 1–5GB file prepared; compression off | Transfer file end-to-end | Sustained throughput >=80MB/s on 1GbE lab or documented cap | >=80MB/s or configured SLO
FIL-009 | FileGet | Backpressure stability | Server artificial slow consumer | Throttle reader to 5MB/s | No agent crash; flow control works; op completes | 0 drops/crash; duration within expected
FIL-010 | FileGet | Expect checksum (pre-known) | Known SHA256 provided in spec | Include expect checksum; transfer | Agent/Server validate against expect; mismatch triggers OpError | Strict validation

## PacketCapture
ID | Category | Test Name | Preconditions | Steps | Expected Result | Metrics / Threshold | Pass/Fail | Notes
PCP-001 | PacketCapture | Start capture with BPF filter | Interface if0 has HTTPS traffic | StartOp(PcapSpec bpf='tcp port 443', duration=10s, snaplen=128) | Receive packets; each orig_len>=captured len; final PcapStats returned | 0 agent crash; stats coherent
PCP-002 | PacketCapture | Structured filter equivalence | Same traffic as PCP-001 | StartOp(StructuredFilter dst_port=443 protocol=tcp) | Packet count close to PCP-001 | Δcount<=1%
PCP-003 | PacketCapture | Packet limit stop | Traffic present | StartOp(... packet_limit=10000) | Op ends automatically with PcapStats | received≈10000±driver variance; duration <= configured
PCP-004 | PacketCapture | Promiscuous mode denial without permission | Agent configured to disallow promisc | StartOp(promisc=true) | OpError(code=promisc_denied) | Proper authorization enforcement
PCP-005 | PacketCapture | Nonexistent interface | Interface name does not exist | StartOp(if_name='bad0') | OpError(code=if_not_found) | Clear error
PCP-006 | PacketCapture | Throughput & stability at high pps | Traffic generator available | StartOp(snaplen=128, duration=30s) under ~100kpps load | No fatal errors; PcapStats.dropped within acceptable range | Drop rate <=1% (or lab baseline)
PCP-007 | PacketCapture | Payload trim enforcement | Generate large packets | StartOp(payload_trim_bytes=64) | Packet data length <=64; orig_len preserved | All packets trimmed to <=64B
PCP-008 | PacketCapture | Periodic progress logs | Enable periodic logging | Observe OpLog every ~5s | Logs include byte/packet counters | Log interval ≈5s±1s
PCP-009 | PacketCapture | Cancel mid-capture | Running capture | Send CancelOp(op_id) | Capture stops <=500ms; final PcapStats emitted | Cancel_latency<=500ms
PCP-010 | PacketCapture | PCAP reconstructability | Collector writes payloads to .pcap | Import into Wireshark | Wireshark opens file; timestamps plausible | File valid; no parser errors

## Exec
ID | Category | Test Name | Preconditions | Steps | Expected Result | Metrics / Threshold | Pass/Fail | Notes
EXE-001 | Exec | Whitelist allowed command | Server whitelist includes 'echo' | StartOp(ExecSpec cmd='echo', args=['hello']) | Receive stdout='hello\n', ExecExit(code=0) | Ack<=500ms; Exit within 2s
EXE-002 | Exec | Blacklist high-risk command | Server blacklist 'rm -rf /' | StartOp(ExecSpec cmd='rm', args=['-rf','/']) | OpAck(accepted=false) or OpError(code='not_allowed') | No execution initiated
EXE-003 | Exec | Timeout enforcement | Command that sleeps 5s | StartOp(timeout=3s) | Process terminated ~3s; ExecExit(code!=0 or note='timeout') | Stop<=3.5s; resources reclaimed
EXE-004 | Exec | max_output_bytes truncation | Command producing large output | StartOp(max_output_bytes=1MB) | Stream stops near limit; ExecExit returned | ~1MB±5%; no crash
EXE-005 | Exec | shell_mode disabled by default | shell_mode policy off | StartOp(shell_mode=true, cmd='sh', args=['-c','echo hi']) | Rejected with not_allowed unless policy permits | Strict default deny
EXE-006 | Exec | RunAs denied without policy | No run_as permission | StartOp(run_as_user='nobody') | OpError(code='runas_denied') | Proper authorization
EXE-007 | Exec | RunAs allowed with policy | Policy allows run_as=nobody | StartOp(cmd='id', run_as_user='nobody') | stdout shows uid/gid of nobody; ExecExit(code=0) | Identity matches policy
EXE-008 | Exec | Interleaved stdout/stderr streaming | Command writes to both streams | StartOp(...); capture chunks | Both stdout/stderr chunks arrive; ordering within stream preserved | No chunk corruption
EXE-009 | Exec | Cancel mid-execution | Long-running command | Send CancelOp(op_id) | Process tree terminated; ExecExit or OpError(cancelled) within 500ms | Cancel<=500ms; no zombies
EXE-010 | Exec | Working directory enforcement | Target dir exists | StartOp(working_dir='/tmp') and run 'pwd' | stdout==/tmp | Correct cwd applied

## Cancel
ID | Category | Test Name | Preconditions | Steps | Expected Result | Metrics / Threshold | Pass/Fail | Notes
CAN-001 | CancelOp | File transfer cancel + resume | FIL-001 running | Send CancelOp; then resume with offset | Stops within 500ms; resume succeeds; checksum OK | Cancel<=500ms
CAN-002 | CancelOp | Capture cancel latency | PCP-001 running | Send CancelOp | Final stats returned; resources released | Handles closed; memory stable
CAN-003 | CancelOp | Exec cancel latency | EXE long task running | Send CancelOp | Process tree exited; no zombies | 0 orphaned procs
CAN-004 | CancelOp | Cancel nonexistent op | No such op_id | Send CancelOp(unknown id) | Agent no-op; maybe OpError(code='op_not_found') | Graceful handling
CAN-005 | CancelOp | Concurrent cancels | Multiple ops running | Cancel several ops quickly | All targeted ops stop; unrelated ops unaffected | Isolation verified

## Reconnect
ID | Category | Test Name | Preconditions | Steps | Expected Result | Metrics / Threshold | Pass/Fail | Notes
RCN-001 | Reconnect | Auto reconnect with backoff | Network drop simulation | Disconnect for 10s; restore | Agent reconnects (exp backoff) and sends AgentHello | Rejoin<=30s; jitter acceptable
RCN-002 | Reconnect | Server session replacement | Agent open old stream; reconnect opens new | Detect new connection; server replaces old; cleans state | Old stream closed; no duplicate processing | Single active session
RCN-003 | Reconnect | Resume policy for FileGet | One file transfer disrupted mid-way | On reconnect, server resumes with offset | Transfer completes; checksum OK | Seamless resume
RCN-004 | Reconnect | Queued StartOps flush after reconnect | Server has pending ops for agent | After reconnect, server dispatches queued ops | Ops execute as expected | No lost ops
RCN-005 | Reconnect | Reconnect storm resilience | Simulate 1000 agents reconnect at once | Observe server health | No crash; rate-limits applied; acceptable latency | CPU/mem within planned SLO

## Security
ID | Category | Test Name | Preconditions | Steps | Expected Result | Metrics / Threshold | Pass/Fail | Notes
SEC-001 | Security | mTLS required | Agent with invalid cert | Attempt connect | Connection rejected at TLS handshake | No plaintext; audit entry logged
SEC-002 | Security | Expired certificate | Agent cert expired | Attempt connect | Rejected; reason=expired | Clear error; audit record
SEC-003 | Security | Revoked certificate (CRL/OCSP) | Cert in CRL | Attempt connect | Rejected; reason=revoked | CRL/OCSP checked
SEC-004 | Security | Tenant isolation | Multi-tenant setup | Send StartOp with tenant A to agent of tenant B | Operation refused; not routed across tenants | Strict isolation
SEC-005 | Security | Audit completeness | Any op executed | Inspect audit DB | Audit contains timestamp, actor, tenant, agent_id, op_id, spec summary, result | All fields present
SEC-006 | Security | Path whitelist enforcement | Whitelist=/var/log only | Attempt FileGet /etc/shadow | OpError(path_denied) | No read outside
SEC-007 | Security | Command injection prevention | shell_mode disabled | Try cmd with metacharacters without shell_mode | Interpreted as argv; no shell expansion | Safe argv handling

## Observability
ID | Category | Test Name | Preconditions | Steps | Expected Result | Metrics / Threshold | Pass/Fail | Notes
OBS-001 | Observability | Prometheus metrics exported | Monitoring enabled | Scrape /metrics | ops_inflight, ops_total, op_duration, bytes_sent_total exist | Names/labels documented
OBS-002 | Observability | Per-op metrics labeled | Run file/pcap/exec ops | Check metrics labels type, code | Metrics split by type and code | Useful cardinality
OBS-003 | Observability | Key alerts configured | Alert rules loaded | Induce repeated failures (not_allowed/timeouts) | Alerts fire as expected | Noisy alerts under control
OBS-004 | Observability | Structured logs with op_id | Run mixed workload | Inspect logs | All logs include op_id/agent_id/tenant | Correlatable logs
OBS-005 | Observability | Backpressure visibility | Throttle server consumer | Observe metrics/logs | Backpressure indicators present (queue depth/blocked writes) | Actionable signals

## Performance
ID | Category | Test Name | Preconditions | Steps | Expected Result | Metrics / Threshold | Pass/Fail | Notes
PRF-001 | Performance | File throughput baseline | 1GbE lab; 4-core agent | Transfer 1–5GB file (no compression) | Throughput >=80MB/s or documented target | >=80MB/s
PRF-002 | Performance | Compression efficiency | Highly compressible log | Repeat transfer with compress=true | Bytes on wire reduced ≥30% | >=30% reduction
PRF-003 | Performance | Exec latency | Simple echo command | Measure time from StartOp to first stdout chunk | Latency <=200ms | <=200ms
PRF-004 | Performance | Pcap sustained pps | Traffic generator ~100kpps | Run 30s capture | No crash; dropped<=1% (or baseline) | <=1% drop
PRF-005 | Performance | Concurrency stress | Allow 10 concurrent ops | Run mixed ops concurrently for 10min | No leaks/crash; p95 op duration within 2x baseline | Resources stable
PRF-006 | Performance | 24h soak | Continuous mixed workload | Run for 24h | FD/memory stable; no panics; reconnects recovered | No leaks; errors<0.1%

## Invariants
ID | Category | Test Name | Preconditions | Steps | Expected Result | Metrics / Threshold | Pass/Fail | Notes
INV-001 | Invariants | Per-op lifecycle | General | Execute any op | Exactly one OpAck then 0..N data/log/progress then exactly one OpEof or OpError | State machine satisfied
INV-002 | Invariants | File chunk monotonicity | FileGet | Record offsets | Offsets strictly increase; no overlap | Monotonic
INV-003 | Invariants | Error terminality | General | Force an error | After OpError no further messages for same op_id | Terminal behavior
INV-004 | Invariants | Cancel responsiveness | General | Issue CancelOp on running op | Stop within 500ms | <=500ms
INV-005 | Invariants | Tenant/actor propagation | General | Start op with tenant+actor | All logs/metrics carry tenant+actor | Consistent propagation
INV-006 | Invariants | Duplicate StartOp handling | General | Send same op_id twice | Second rejected as duplicate | No double execution

## Overview
Section | Goal | Key Success Criteria
Control | Server-initiated ops over single bidi stream | Ack<=500ms; concurrency>=5; heartbeats reliable; idempotency works
FileGet | Reliable, resumable, verifiable file streaming | Checksum match; resume by offset; whitelist enforced; >=80MB/s baseline
PacketCapture | Filtered, bounded, and reconstructable capture | Filter accuracy<=1% delta; limit/duration respected; Wireshark opens
Exec | Safe, audited, resource-bounded command exec | Whitelist/blocklist enforced; timeout/truncation; runAs policy respected
Cancel | Responsive cancellation semantics | All ops stop<=500ms; resources reclaimed; resume where applicable
Reconnect | Graceful reconnect/queue handling | Hello on reconnect; queued ops flush; file resume works
Security | mTLS + tenancy + least-privilege | TLS rejects bad/expired/revoked; tenant isolation airtight
Observability | Metrics/logs/audit for SRE use | Per-op metrics; alerts fire; logs carry op_id/agent_id/tenant
Performance | Throughput/latency/stability SLOs | 80MB/s file; 100kpps pcap; <=200ms exec latency; 24h soak stable
Invariants | Protocol behavior guarantees | Exactly-once ack; terminal errors; monotonic chunks; cancel SLA